## Slide 1: KSIDC Action Plan 2022 - 23 (Systems/ Goals/ Programs of KSIDC)
Harikishore S, MD KSIDC
Date 04-02-2023

## Slide 2: Index
Sl. No | Name of the team | Number of action points
1 | Investment Facilitation | 17
2 | Investment Promotion | 16
3 | Project Finance | 8
4 | We mission and Start up | 2
5 | Infrastructure Development | 11
6 | Waste to Energy | 2
7 | Sabarimala Airport | 4
8 | HR and Admin | 6

## Slide 3: Team 1 - Investment Facilitation
Varghese M (AGM)
Ratheesh S (AGM)
Zubin Joseph , KPMG
Sabari Viswambaran, KPMG
Aiswarya Krishnan, KPMG
Rahul Jagadish ,BDE
Liju John, BDA
Aanad ,BDE
Parvathy, BDE

## Slide 4: 1. Investor Tracker -Dedicated person, phone number and email to track investments (Parvathy M L, investments@ksidcmail.org)
Year | Number of investors contacted | Number of investors for whom all supports provided | Converted to investments
2021- 22 | 0 | 0 | 0
2022 - 23 | 30 | 6 | 1
2023 - 24 | 8 | Clearances from various departments are being facilitated | 
2024 - 25 |  |  | 

## Slide 5: 2. KSWIFT monitoring system- The goal is to ensure timely clearance of new applications by calling applicant and departments(Rahul, BDE)
Month | Total applications | Total Calls | Disposed during the month | Disposed during the next month | Total disposed | % | Balance
Aug | 165 | 200 | 15 | 81 | 96 | 58.18 | 69
Sept | 138 | 148 | 10 | 44 | 54 | 40 | 84
Oct | 228 | 212 | 13 | 0 | 13 | 5.70 | 215
Nov | 146 | 120 | 08 | 28 | 36 | 24.65 | 110
Dec ‘22 | 142 | 152 | 13 | 27 | 40 | 28.16 | 102
Jan ‘23 | 124 | 90 | 07 | 02 | 09 | 7.25 | 115

## Slide 6: 3. KSWIFT one time effort to clear backlogs The goal is to clear all backlog applications in three months, (Rahul Jagadish BDE)
Sl. No. | Description | 
1 | Total number of applications in KSWIFT from Feb 2019 | 4,891
2 | Sanctioned till August 1, 2022 | 2,502
3 | Balance old applications | *28
4 | Cleared in August | 74 (29%)
5 | in September | 51 (20%)
6 | in October | 41 (16%)
7 | in November | 21(8.30%)
8 | in December ‘22 | 20(7.9%)
9 | in January ‘23 | 16(6.32)
10 | Total Result | 
* During the review meeting held on 12.09.2022 with JD, Panchayat, it was decided that the long pending applications with Grama Panchayats has to be closed after hearing the respective Panchayats. There were 253 pending applications. Accordingly Directorate of Panchayats has forwarded the list of pending applications with appropriate reasons for closing on 17.09.2022. NIC, on 19.09.2022, was directed to make necessary changes in the portal to close such cases.

## Slide 7: 4. KSWIFT - Solving issues in the software (Total 22 issues)
Sl. No. | Issues Identified | Action taken till Sept 15 | Timeline to complete | Result
1 | GM DIC’s should be able to view query/ answer in the application workflow of departments | Discussed with NIC & necessary modifications are being done | 30 Dec 22 | The provision made available
2 | Contact details of Project Executives to be made available in the portal |  | 15 Sep 22 | Contact details of Project Executives uploaded in the K-SWIFT portal

## Slide 8: 4. KSWIFT - Solving issues in the software
Sl. No. | Issues Identified | Action taken till Sept 15 | Timeline to complete | Result
3 | Deemed license on the applications submitted to Agriculture Dept | Discussed with AD (Agriculture Dept.). It was informed that the workflow in K-SWIFT is being familiarized by the Dept. officials. Further the Dept. is organizing one more training session for their officials handling K-SWIFT and then will decide on modifying the workflow for deemed issuance of licenses | 30 Dec 22 | Provision made available for license to store/ sell fertilizer
4 | Edit option for the application submitted for Acknowledgement certificate |  | 31 Dec 22 | Decided not to provide edit option

## Slide 9: 5. KSWIFT - Onboard new services
Sl. No. | Action Plan | Time line | Result
1 | Identify new services to be onboarded to KSIWFT | 15 Sept | 11 new services of 6 departments identified
2 | Prepare strategy and road map/ action plan to onboard services | 15 Oct | Listed out services/ departments and shared with NIC
3 | Start onboarding process | 1 Nov | Integrated 4 services of Forest & Wildlife Dept. Integrated new web portal of KSPCB
4 | Complete onboarding of 11 services | 31 Mar | 

## Slide 10: 6. KSWIFT - Communication Plan
Sl. No. | Action Plan | Time line | Result
1 | Prepare videos to create awareness on KSWIFT | 15 Oct 2022 | 11 videos ready
2 | Conduct promotional campaign from Dec ‘22 to March ‘23 | Oct 2022 | Advt. video campaign started in Dec ‘22 and still on
3 | Conduct training session for all LSG’s/ interns (in 14 districts) | 31 Dec 2022 | Conducted 4 training sessions
4 | Advt. through Hoardings, train advt. boards/ digital kiosks, print media | Nov 22 - March 23 | Campaign started and still on. Advt. through hoardings to be finalized.

## Slide 11: 7. Policies for Ease of Doing Business (68 policies)
Sl No | Department | No of Interventions | Sl No |  | 
1 | Agriculture Development | 2 | 10 | Industries | 16
2 | Drugs Control/ Ayush | 2 | 11 | IT | 6
3 | Excise | 1 | 12 | KCZMA | 1
4 | Factories and Boilers | 3 | 13 | Labour and Skills | 4
5 | Fire & Rescue | 2 | 14 | LSGD | 8
6 | Forest & Wildlife | 1 | 15 | Mining & Geology | 2
7 | General | 8 | 16 | KSPCB | 2
8 | Health | 2 | 17 | Tourism | 6
9 | FSSAI | 1 | 18 | Irrigation | 1

## Slide 12: 8. Kerala Single Window Clearance Board
Year | No of board meetings held | No of proposals
2018 | 3 | 9
2019 | 2 | 5
2020 | 4 | 13
2021 | 2 | 4
2022 | 4 | 7
First meeting held on 08.06.2000
33 meetings held so far
23 Applications pending

## Slide 13: 9. Call Centre (1800-890–1030)/ Started in 2020 Sep/ 8 AM to 8 PM/ 6 executives/ Operated by M/s Aabaasoft/ (~600 calls per month)
No | Category of calls | Total No | %
1 | K-SWIFT Enquiries | 7,012 | 43.31
2 | Miscellaneous | 3,701 | 22.86
3 | K-SWIFT Technical | 1,876 | 11.59
4 | Starting a Business | 1,654 | 10.21
5 | Funding Assistance | 1,298 | 8.02
6 | Local Protest/ Political issues | 342 | 2.11
7 | Land Bank/ Land related issue | 203 | 1.25
8 | Schemes & Policy related | 106 | 0.65
 | Total | 16,192 | 

## Slide 14: Call Centre (1800-890–1030)/ Started in 2020 Sep/ 8 AM to 8 PM/ 6 executives/ Operated by M/S Aabaasoft/ (~600 calls per month)
Sl. No. | Action Plan | Time line | Result
1 | Data Analysis | 31 Aug | Completed on 26 Aug 22
2 | Training to Executives | 1st week of March ‘23 | 
3 | Special 4 Digit toll free number | 1 Nov | Not feasible
4 | Redefine data capturing fields | Sept ‘23 | CRM module with token provision

## Slide 15: 10. SBRAP 2022 (352 reforms/ 22 departments/ agencies)
Time line | Completed (Out of 352) | Proofs Pending from Departments | Proofs received for review | Proofs uploaded in portal
29 Aug '22 | 260 (73.86%) | 99 (28.12%) | 161 (45.73%) | 25 (7.10%)
15 Sep '22 | 271 (76.98%) | 76 (21.59%) | 195 (55.39%) | 92 (26.13%)
31 Oct '22 | 324 (92.00%) | 28 reforms cannot be implemented received all other | 32 (9.00%) | 292 (83.00%)
30 Nov ‘22 | 340 (96.59%) |  |  | 340 (96.59%)
Proofs for 340 reforms uploaded in DPIIT portal
Evidence scrutiny started by DPIIT
122 sets of beneficiary data uploaded in the portal for feedback survey

## Slide 16: SBRAP 2022 - Action Plan- User Feedback improvement strategy
Month | Action Item | Result
Nov | Training of the call centre executives on the questionnaires in line with the service availed by the user | Completed
Nov | Collating user list shared by the departments. User list shall be approximately around 4500 number | Uploaded 122 sets of beneficiary database to DPIIT portal (20, 968 numbers)
Dec ‘22 | Telephonic survey by Call Centre | Reached out to beneficiaries through Invest Kerala Helpdesk Call Centre
Jan ‘23 | Sensitize Nodal officers, preparation of action plan for feedback survey | Meeting of Nodal Officers under the Chairmanship of Principal Secretary, Industries held on 25.01.2023
Feb | Department level feedback survey | All departments submitted action plan on 03.02.2023
Feb | Departments to complete survey by 20.02.2023 | 

## Slide 17: 11. PM Gati Shakti
The Union Government has allocated an amount of Rs 1 lakh crore for the Scheme named ‘Special Assistance to States for Capital Investment for 2022-’23’
Scheme for
  Capital works (PM Gati Shakti related projects gets priority) – Rs. 1,540 Cr
  PM Gati Shakti related expenditure – Rs. 96.25 Cr
50 year interest free loan for capital investment

## Slide 18: PM Gati Shakti
28 out of 30 Mandatory Data Layers integrated with BISAG-N Portal |  |  |  | 
Action Plan for Remaining 7 Data Layers |  |  |  | 
Sl.No | Data Layer | Department | Timeline | Result
1 | Eco sensitive zones | Forest & Wildlife | Waiting for notification of the zone limits by MoEF, GoI (Oct 2022) | Completed
2 | Embankments | Irrigation/ | Oct 2022 | 
3 | Sewer Lines | LSGD (Urban) | Oct 2022 | Completed
4 | Electric Poles | KSEB | Oct 2022 | Completed
5 | Traffic Light Poles | MVD | Oct 2022 | Completed
6 | Fuel dispensing stations | Various agencies |  | Completed
7 | Village habitations | Revenue |  | Partially uploaded

## Slide 19: PM Gati Shakti -Additional Data Layers Integration
S. No | Data Layer | Department | Integration Status
1 | Optic Fibres | KFON | Yes
2 | Ports | Ports Department | Yes
3 | Cattle Feed centres | Animal Husbandry | Yes
4 | Sabarimala Airport | KSIDC | Yes
5 | Agriculture Weather Stations | Agriculture | Yes
6 | Pack Houses | Agriculture | Yes
7 | Seed production plants | Agriculture | Yes
8 | Training centers | Agriculture | Yes
9 | Cattle Feed Warehouses | Animal Husbandry | Yes
10 | Cattle farms | Animal Husbandry | Yes
11 | Flood probability areas | Disaster Management | Yes
12 | Land slide prone areas | Disaster Management | Yes
13 | Fish Landing Centres | Fisheries | Yes
14 | Hatcheries | Fisheries | Yes
15 | Sports complexes | Sports | Yes
16 | Inland Waterways | Water Resources | Yes

## Slide 20: PM Gati Shakti - Special Assistance Scheme
S.No | Amount in Cr | Action Plan | Timeline | Result
1 | 1,540 | Plan submitted by Finance Dept for Rs 2,665.61 Cr | Aug 2022 | Submitted
2 | 96.25 | First set of 2 projects briefed with DPR (Petrochemical + Life Sciences park ) to be shared with DPIIT | Oct 2022 | Completed
 |  | Next set of Project brief documents to be collated from dept | Oct 2022 | Completed
3 |  | State Master Plan | Nov 2022 | Submitted

## Slide 21: Special Assistance Scheme -Tentative List of Projects
SlNo | Department | Projects | Project Components | DPR submission date | Result
1 | Industries | Life Sciences Park | Road Infrastructure ETP Animal House Purchase of Equipment | Nov 2022 | Rs. 15 Cr. Received from GoI on 15.12.2022
3 | Industries | Petrochemical Park | Roads 4 lane Potable water distribution system Effluent Conveyance System | Nov 2022 | Rs. 55 Cr. Received from GoI on 15.12.2022
3 | IT | KSDI | 1. K-GIS | Nov 2022 | Rs. 6 Cr. Received from GoI on 15.12.2022
4 | Industries | DIC | 1. Various components (Road, compound wall, street light, etc.) | Nov 2022 | Rs. 20 Cr. Received from GoI on 15.12.2022

## Slide 22: 12. External Committee for Legislative Reforms
Slno | Month | Action Plan | Result
1 | Sep | Form a team of Research Scholar & Retired AS, Law Joint meetings with Minister (Industries) with Ministers in charge of Power, Environment, Revenue , Civil Supplies & Registration Send proposal for setting up 6 working Committees | Requested date for LSGD,labour and Industries working group.
2 | Oct | Conduct 6 Working Committee Meeting Joint meetings with Minister (Industries) with Ministers in charge of Home, Excise, Forest, Water Resources & Agriculture Send proposal for setting up 6 working Committees | Working Committee meeting for Labour Department scheduled for 2nd week of Feb ‘23
3 | Nov | 1. Conduct 6 working committee meetings | 
4 | Dec |  | 

## Slide 23: 13. K-CIS (Kerala Centralised Inspection System ) - launched in July 2021
Scheduling of statutory inspections, based on risk category, by randomized selection of enterprises and inspectors
5 Departments onboarded-LSGD, KSPCB, Legal Metrology, Factories & Boilers, Labour Department
Slno | Description | Remark
1 | Total enterprises listed in the system | 5,02,071
2 | Number of inspection scheduled | 16,430
3 | Inspections Conducted | 9,411
4 | Complaints received | 44

## Slide 24: K-CIS
Slno | Action Plan | Timeline | Result
1 | Developing strategy to improve efficiency of KCIS | Jan 2023 | 
2 | Developing action plan to expand KCIS by adding more Department & Enterprises | Dec 2022 | 
3 | Training to officials of KSPCB | 15 Oct 2022 | 
4 | Populating list of enterprises based on list by LSGD | Nov 2022 | 
5 | Modification in K-CIS to facilitate joint inspection (factories and boilers and labour) | Oct 2022 | Implemented

## Slide 25: 14. Logistics Ease Across Different States (LEADS)
Slno | LEADS Indicator | Action Point | Departmentt | Action plan | Timeline | Result
1 | Availability and quality of infrastructure | Upgradation of road infrastructure | LSGD | Logistic action plan to be prepared | Oct 2022 | 
2 | Availability and reliability of logistics service | Enhance safety & security at terminals | Ports-Cochin Port | Discussion with CPT | Nov 2022 | 
3 | Operating and regulatory environment | Easing regulatory approvals | Various Depts. | Discussion with Depts. | Dec 2022 – Jan 2023 | 
2018 – Rank 12
    2019 – Rank 11
    2021 – Rank 14

## Slide 26: Logistics Ease Across Different States (LEADS)
Sl. No | LEADS Indicator | Action Point | Department | Action plan | Timeline | Result
4 | State Logistics Eco System | Convene meeting of Logistics coordination committee |  | Meeting with stakeholders | Oct 2022 | 
5 | Issues & Challenges | Lacks of storage capacity at Cochin Port trust | Cochin Port | Share letter to Cochin Port on the issue raised |  | Shared letter to Cochin Port
6 | Develop strategy for improving ranking |  |  |  | Jan 2023 | 

## Slide 27: 15. Minimizing Regulatory Compliance Burden (RCB)
Aimed to minimize physical touchpoints between G2B and G2C
In SBRAP exercise DPIIT mandates action points to be implemented by states, whereas in Minimising RCB exercise, Departments/ Agencies to identify cumbersome procedures for minimising
There is no state ranking for this exercise

## Slide 28: Minimizing Regulatory Compliance Burden
Business |  |  |  | 
Month | Reforms Identified | Reduced | Pending | %
Till Aug 2022 | 920 | 610 | 310 | 66.30
Sep 2022 | 934 | 620 | 314 | 66.38
Oct 2022 | 937 | 626 | 311 | 66.81
Nov 2022 |  |  |  | 
Dec 2022 |  |  |  | 

## Slide 29: Minimising Regulatory Compliance Burden
Citizen |  |  |  | 
Month | Reforms Identified | Reduced | Pending | %
Till Aug 2022 | 1,316 | 1,294 | 22 | 98.48
Sep 2022 | 1,324 | 1,294 | 30 | 97.73
Oct 2022 | 1,324 | 1,302 | 22 | 98.33
Nov 2022 |  |  |  | 
Dec 2022 |  |  |  | 

## Slide 30: 16. Publish Editorial Articles on Kerala Achievements on IF
Slno | Reform Area from Citizen Perspective | Topics | Media Type | Timeline | Result
1 | Business/ Citizen | To identify the reforms from a citizen point of view which created maximum impact in the ‘Ease of Doing Business’ or in the ‘Ease of Living’ initiatives by the government for media coverage. | Magazine,News Paper | Jan 23 | 
2 | Employment Exchange | Providing Registration & Renewal of job seekers on employment exchange through the online single window system. | Cochin Port | Jan 23 | 

## Slide 31: Media Articles
Slno | Reform Area from Citizen Perspective | Topics | Media Type | Timeline | Result
3 | Online Connection | Following services are provided through the online single window system -water connection, Electricity, State health card, Driving license | Magazine,News Paper,Digital media | Jan 23 | 
4 | Online Certificates | Following certificates are provided through the online single window system-Birth & Death certificate, Income certificate, caste certificate, marriage certificate, Domicile certificate, caste certificate | Magazine,News Paper,Digital media | Jan 23 | 

## Slide 32: Team 2 - Investment Promotion
1. | Ashok Lal GM I/c | 6 | Shobin Das ,BDE
2 | Dr Sebastian Thomas, AGM | 7 | Priya Prasad, BDE
3 | Vineeth V, Assistant Manager | 8 | Jithin P V,BDE
4 | Feleeshia Sabu , BDE | 9 | Kavitha K,BDE
5 | Sabrina AR, BDE | 10 | Danesh,BDE

## Slide 33: 1. Investment Promotion -7 Pronged Strategy/ Action Plan
Sl. No | Goal | Result
1 | Prepare IP roadmap for Kerala by August 31st and get approval | Completed
2 | Select 10 BDE’s for supporting IP –by Oct | Sabrina joined 01/12/22 Piya joined 28/12/22 Jithin & Shobin Joined 04/01/23 Kavitha Joined 13/01/23 Dhanesh joined 23/01/23
3 | Take Action as per the approved detailed action plan-Oct to March | 
4 | Select IP Team (Total 37) | A detailed reply has been sent to the industries department on vide their letter dated 23.12.2022 sought clarifications for the request.

## Slide 34: 2. Investment-Follow up
Sl. No | To Do | Timeline | Result
1 | IBPC visit to Kerala | Oct 22 | Was scheduled on 04.11.2022; stands postponed as of now.
2 | Canada-India Business Council Meeting | 24.11.2022 | Meeting held at Trivandrum. We have to participate in their upcoming event in Bangalore on 14.03.2023. A follow-up letter in this regard has been sent.
3 | Land to Muralya & Hotpack | Sep 22 | Done

## Slide 35: 2.Investment-Follow Up
Sl. No | To Do | Timeline | Result
4 | Individual follow-up of Enquiries | Sep 22 | Being done by IF
5 | Meeting with Terje Neras, CEO, Chief Executive Officer, Maritime Monitering Group, Norway |  | Minister level meeting was conducted on 17.01.2023 at Kochi. Asked to submit detailed proposal with specific requirement or support they would need from GOK. KSIDC IP division have formulated a policy for Maritime sector and submitted to IF division of KSIDC (handling the Draft Industrial Policy)

## Slide 36: 3. PR Agency
Month | Press Release (Target 4 per month) | Special Story in National Daily(Target 1 per month | Covering Events(As and when there is event)
Aug | 2 Nos | 2 Nos | 1 No
Sep | 2 Nos | -- | 3 Nos
Oct | Nil | Nil | Nil
Nov | Nil | Nil | Nil
Steps initiated to onboard the agencies already empaneled by PRD and Tourism Department. Board Note submitted to be placed for the upcoming board meeting. |  |  | 

## Slide 37: 4 . ESG -Goal is to develop a ESG framework and RI Classification
Sl. No | Action Plan | Timeline | Result
1 | Discussion of proposal with Digital University | Sep 22 | Discussed on 31st August
2 | Approval of Proposal & setting up team | Nov 22 | DUK submitted a draft proposal. Sent a proposal to GoK on 11.10.2022 requesting to form an expert committee with members consisting of Mr.Akshay Mangala (Oxford Uty), Dinesh Nirmal (IBM), CJ George (Geojith) & S.Harikishore IAS (KSIDC) as members. G.O. received on 05.11.2022. The 1st Meeting of the Expert Committee scheduled for 20.12.2022 at 4.00 pm (IST) via online, conducted on 16th of January 2023. Next meeting scheduled on 09th February 2023 at Kochi
3 | Developing ESG framework & RI Classification | April 23 | 
4 | Rollout of RI Classification scheme | May 23 | 

## Slide 38: 5. Growth Lab for Scale up ( With Digital University )
Sl. No | Action Plan | Timeline | Result
1 | Discussion and approval of proposal | Sep 22 | Discussion imitated with DUK
2 | Growth lab for 30 CEO’s | Nov 22 | Discussed with CII for identifying the participants; Concept note to be shared. Scheduled for the last week of February 2023. Meeting held with DUK on 10.01.2023. List of companies has been shared to them.
3 | Second lab for 30 CEO’s | Feb 23 | Pushed to March/April 2023

## Slide 39: 6. Communication Campaign-Phase 1
Sl. No | Action Plan | Timeline | Result
1 | Success stories of 28 startups | Sep 22 | Only 18 videos made. High-resolution files in pen drive received.
2 | Videos of 50 Industries | Nov 22 | Work order issued on 23.09.2022 to C-DIT and provided the complete list of companies on 08.11.2022. C-DIT had to complete the work by 01.12.2022. After an elapse of 27 days, on 28.12.2022, C-DIT informed that they need an advance payment of 50%. This work is expected to be further delayed.
3 | Two Special campaign through agencies | Dec 22 | Issued Work Order on 24.09.2022 and provided necessary inputs to M/s Stark and M/s Jelitta. Received the 20 Static and 15 Motion Posters. Expected to be delivered by 15th February 2023.
4 | Selecting in-house design/content team | Oct 22 | Content creator cum writer joined in IP team on 1st Dec 2022. Two Content Developer and a Designer joined on 05th January 2023.

## Slide 40: 7. Communication Campaign-Phase 2
Sl. No | Action Plan | Timeline | Result
1 | Selection of Agencies | Dec 22 | E-file put up.
2 | PR/Communication Strategies for industries | Feb 23 | E-file send to MD. But decide to submit the proposal in the Board Meeting (On board the agencies empaneled by PRD and Tourism Department )
3 | Implementing long term strategy | March 23 onwards | TBD

## Slide 41: 8. Action Plan for Branding Kerala -IP Strategy 1
Sl. No | Action Plan | Timeline | Result
1 | New logo and tag line | Nov 22 | Released the new logo and tagline on 18.01.2023
2 | New Invest Kerala site | Nov 22 | Mapped the website requirement vis-à-vis the existing website done through KPMG (in 2019 for a cost of Rs.35.00 lakhs). As the amount is estimated to be above 5 Lakhs, e-tender is being floated. The Draft RFP send for approval from IT Mission Kerala. E-file put up.
3 | Campaign with videos/poster/handout | Oct to Dec 22 | Expected to be ready by 15th January 2023
4 | Sectoral Videos and Brochures | Dec 22 | Work Order to be issued by February 1st Week to Stark as the logo and tagline are finalized.
5 | Attending 10 trade fairs and roadshows |  | See the next slide
6 | International PR |  | G.O received for attending the International trade fair and business meeting in UAE, Korea, Israel, and Ireland.

## Slide 42: 8. Action Plan for Branding Kerala -IP Strategy 1 (Cont.)
Sl. No | Action Plan | Timeline
1 | Meeting with Ambassadors of different countries | 18th October 2022
2 | Meet the Minister & Interface with investors in Wayanad | 21st November 2022
3 | Draft Industrial Policy- presented to the Stakeholders of KSSIA | 24th November 2022
4 | Meeting with Canada - India Business Council | 24th November 2022
5 | Invest India Meeting at Delhi | 23-24 December 2022
6 | Industry and Business Engagement Roundtable with AIBC | 11th January 2023

## Slide 43: National Roadshows & Trade Fairs Attended
Sl. No | Name of the Event | Date | Location | KSIDC Role
1 | Start-Up Conclave | 28th Sept | Trivandrum | Organizer
2 | CII Kerala Smart Mobility Summit | 19th Oct | Kochi | Participant
3 | FICCI Made in Kerala Award | 10th Dec | Kochi | Provided sponsorship
4 | Kochi Design Week | 16-17 Dec | Kochi | KSIDC Stall
5 | Evolve (International Conference and Expo on E-Mobility and Alternative Fuels) | 19-22 Jan 2023 | Trivandrum | Participant
6 | Samrambhaka Mahasangamam | 21st Jan 2023 | Kochi | Participant & KSIDC Stall
7 | India Boat and Marine Show 2023 | 27-29 Jan 2023 | Kochi | KSIDC Stall

## Slide 44: 9. Action Plan for Sectorial Approach -IP Strategy 2
Sl. No | Action Plan | Timeline | Result
1 | Conducting 6 sectorial discussions | Sep 22 to Oct 22 | Completed 6 Sectoral meetings by 29th Nov 2022 (See the next slide)
2 | Data research for each sector | Oct 22 to Nov 22 | Initiated & KSIDC officers made ppt on 15.10.2022 and detailed sectoral report is being compiled by the respective officers; to be ready before 31.12.2022
3 | Developing sectorial strategy for long term | Dec 22 to Jan 23 | RFP to be floated to find a suitable agency.
4 | Implementing | Feb 23 onwards | TBD

## Slide 45: 9. Action Plan for Sectorial Approach -IP Strategy 2( Cont.)
Sl. No | Action Plan | Timeline
1 | Graphene Sectoral Meeting | 26th September 2022
2 | Medical Devices Sectoral Meeting | 27th October 2022
3 | Electronics Sectoral Meeting | 23rd November 2022
4 | Aerospace and Defense Sectoral Meeting | 24th November 2022
5 | Food Sector Meeting | 28th November 2022
6 | Maritime Sector Meeting | 29th November 2022

## Slide 46: 10. Action Plan for Attracting Foreign Investments -IP Strategy 3
Sl. No | Action Plan | Timeline | Result
1 | Initial planning/database of anchor investors |  | To be initiated
2 | Scheduling one to one meeting(at least 10 this year) |  | TBD
3 | Participating in international events(at least 5) | Dec to Jan | Attended Medica 2022 from 13-16 November 2022 in Dusseldorf, Germany. Attended Arab Health from 30th Jan 2023 to 1st Feb 2023 in Dubai. (G.O obtained for participation in 4 events till 31.03.2023, as per the list in the next slide)

## Slide 47: G.O. Obtained International Events in 2022-2023
Sl. No | Event | Location | Tentative Travel Date | Status
1. | ARAB HEALTH EXPO 2023 & Roadshow | Dubai | 30th January 2023 to 2nd February 2023 | Arab Health attended. Travel permission yet to be received
2. | SEMICON 2023 | Seoul, South Korea | 1-3rd Feb 2023 | 
3. | Agri Tech 2023 & Roadshows | Israel | 2-5th May 2023 | Letter to be sent for travel permission
4. | Roadshow | Ireland | 8-11th June 2023 | 

## Slide 48: 11. Action Plan for Targeting NRK Investments- IP Strategy 4
Sl. No | Action Plan | Timeline | Result
1 | Creation of NRK data base | Nov 22 to Dec 22 | Initial List Ready
2 | Events in all GCC(5 road shows) | Jan 23 to Feb 23 | Proposal to be submitted to GoK
3 | Special Communication campaigns | Jan23 to Feb 23 | (TBD) Investor Meet scheduled on 30th January 2023
4 | IP desk in Dubai | March/April 23 | Will be taken up during the Investor Meet scheduled on 30th January 2023

## Slide 49: 12. Action Plan for Leveraging Invest India -IP Strategy 5
Sl. No | Action Plan | Timeline | Result
1 | Visit to Invest India | Oct 22 | Invest India team visited on Oct 2022 and 21st December 2022
3 | Participating Invest India shows | March 2023 | Being collected
4 | Updating projects |  | ST Telemedia Details not yet given to the party
5 | Investment desk at Delhi | April 23 | 

## Slide 50: 13. Action plan for Convergence Approach- -IP Strategy 6
Sl. No | Action Plan | Timeline | Result
1 | Discussion with Norka,Tourism etc |  | Attending PBD 2023 at Indore along with NORKA on 9th January 2023.
2 |  |  | 
3 |  |  | 

## Slide 51: 14. Action Plan for Special IP Team (37)- IP Strategy 7
Sl. No | Action Plan | Timeline | Result
1 | Selection | Nov 22 | 6 members were onboarded. A reply has been sent to the industries department vide their letter dated 23.12.2022 seeking clarifications for the request.
2 | Training | Dec 22 | Six BDEs joined and on-the-job training is going on.

## Slide 52: 15. Setting Up of Consultancy wing in KSIDC
Sl. No | Action Plan | Timeline | Result
1 | Initial Discussion | Oct 22 | 
2 | Team Formation | Nov 22 | To be initiated
3 | Getting work order(at least 2 in this financial year) | Jan/Feb 23 | 

## Slide 53: 16. KSIDC Website
Sl. No | Action Plan | Timeline | Result
1 | Work order to redesign | Oct 22 | Relaunched on 18th January 2023.
2 | Launch of new site | Feb 23 | 

## Slide 54: 17. Planning
Sl. No | Action Plan | Timeline
1 | Plan Fund internal discussion | 07.10.2022
2 | Plan Fund discussion with MD | 10.10.2022
3 | Meeting with Planning Division | 28.10.2022
4 | Meeting with Minister for Industries/Principle Secy Industries | 25.11.2022
5 | Plan Space Updation | 05.12.2022
6 | Minister’s Review Meeting | 28.12.2022

## Slide 55: 18. LA Questions (Fifteenth Kerala Assembly, Seventh Session 05.12.2022 – 15.12.2022)
Sl. No | Action Plan | 
1 | Number of Starred Questions received | 17 Nos
2 | Number of Unstarred Questions received | 65 Nos
3 | Submission | 1 Nos
4 | Loksabha Qns | 1 Nos
 | Total | 82 Nos (excluding submission and Loksabha question)

## Slide 56: 19. Additional works done in the Month of Nov/Dec 2022
Sl. No | Action Plan | Date
1 | Meet the Minister & Interface with investors in Wayanad | 21st Nov 2022
2 | Draft Industrial Policy- presented to the Stakeholders of KSSIA | 24th Nov 2022
 | Meeting with Canada - India Business Council | 
3 | Inauguration of Coconut Food Processing Park, Kuttiyadi | 17th Dec 2022
4 | Invest India Meeting in Trivandrum | 21st Dec 2022

## Slide 57: 20. Event Look Ahead Schedule till 31.03.2022
Sl. No | Name of the Event | Date | Location | Status | International/ Domestic
1 | Arab Health Expo 2023 | 25.01.2023 03.02.2023 | Dubai | KSIDC Stall | International
2 | SEMICON 2023 | 01.02.2023 03.02.2023 | South Korea | Nomination Letter to go | International
3 | G-Ex Kerala ‘23 (Global Expo on Waste Management Technologies) | 04.02.2023 06.02.2023 | Kochi | Participant | Domestic
4 | Uttar Pradesh Global Investors Summit (UPGIS) 2023 | 10.02.2023 12.02.2023 | Lucknow | Not decided | Domestic
5 | M4 EXPO 2023 | 21.02.2023 23.02.2023 | Thailand | Not decided | International

## Slide 58: 20. Event Look Ahead Schedule till 31.03.2022 (Cont.)
Sl. No | Name of the Event | Date | Location | Status | International/Domestic
6 | Kerala State Promotion Event | Feb Mid 2023 | Amman, Jordan | Not decided | International
7 | BioAsia2023 | 24.02.2023 26.02.2023 | Hyderabad | Not decided | Domestic
8 | Roadshows in Ireland & Israel |  |  | Letter to Gok to send | International
9 | Power World Expo 2023 | 01.03.2023 03.03.2023 | Mumbai | Not decided | Domestic
10 | Bengaluru Innovation Summit | 14.03.2023 | Bengaluru | Participant | Domestic
11 | 3rd Edition of International SME Convention 2023 | 19.03.2023 21.03.2023 | New Delhi | Participant | Domestic
12 | Expocomer | 28.03.2023 30.03.2023 | Republic of Panama | To be Decided | International

## Slide 59: Team 3 - Project Finance
Thiruvananthapuram | Ernakulam | Calicut
R. Ravichandran ,Deputy General Manager Sini K Thoppil, Asst.General Manager Prasanth Prathap, Deputy Manager | Prasanth R , General Manager I/c Rajesh Jacob, Asst. General Manager Nithesh B, Manager Adel K M, Manager Ashik Sheik, Manager Rithu K S, Deputy Manager | Binil Kumar, Asst.General Manager Jackson Jose, Manager

## Slide 60: Project Finance - Overall status of loan
Book Size : Total principal loan outstanding : Rs.819.65 Crores,
Total units:175
2. Default (NPA) : Total loan outstanding : Rs. 129.81 Crores
Total units : 41

## Slide 61: Project Finance - Historic Performance
No Plan Amount Timeline Result
Specification | Sanctioned Amount(Cr) | No of units | Disbursement | Recovery | Principal | Interest
2017-2018 | 158.88 | 22 | 75.28 | 81.41 | 51.02 | 30.39
2018-2019 | 118.46 | 14 | 64.44 | 85.47 | 56.69 | 28.78
2019-2020 | 302.75 | 24 | 59.52 | 92.03 | 70.25 | 21.78
2020-2021 | 335.26 | 39 | 312.88 | 80.96 | 50.89 | 30.07
2021-2022 | 428.01 | 132 | 287.24 | 148.27 | 98.70 | 49.57

## Slide 62: Loan Schemes of KSIDC – Regular Schemes
Scheme | Scheme Details | Number of units | Sanction (Cr) | Disbursements(Cr)
Term Loan | Quantum: Rs.1 Cr-60 Crs. Interest : 9.20% - 11.20% Moratorium up to 3 Yrs Repayment up to 10 Yrs | 79 | 738.53 | 647
Working Capital Term Loan | Quantum: Rs.1 Cr-25 Crs. Interest : 9.20% - 11.20% Repayment 5-8 Yrs | 0 | 0 | 0
Equipment loan | Quantum: Rs.1 Cr-20 Crs. Interest : 9.20% - 11.20% Repayment 5-8 Yrs | 3 | 14.56 | 14.20
Corporate loan | Quantum: Rs.1 Cr-40 Crs. Interest : 9.20% - 11.20% Moratorium up to 6-12 m Repayment up to 5-8 Yrs | 6 | 113.10 | 88.56

## Slide 63: Project Finance – Special schemes
Contd.
Scheme | Scheme details | Number of units | Sanction (Cr) | Disbursements (Cr)
CM Special Assistance Scheme | Quantum: Rs.25 lakhs to Rs.200 lakhs Interest rate: 9.2% (Lowest of interest bank) and 3% interest subvention from GoK Repayment period: up to 6 years -1 year moratorium | 22 | 29.40 | 20.51
Vyavasaya Bhadratha | (Sanction Discontinued)-Special package and Relief Schemes for MSMEs (Top up Working Capital term loans with interest of 5% of up to Rs. 2 Crores to existing standard clients of KSIDC) to overcome the impact of first wave COVID 19. | 16 | 20.14 | 20.14
Covid Samaswasa Padhathi | (Sanction Discontinued)-Continued package & Relief Schemes for MSMEs (Additional Working Capital Term Loan with interest of 5% from 25Lakhs to Rs. 2 Cr) | 88 | 130.00 | 126.00
Bill Discounting scheme | For discounting of pending bills with treasury For Class A & B contractors Quantum:up to 80% contract value limited Rs.5 cr Interest rate: Highest rate in the interest band | 2 | 6.63 | 2.67

## Slide 64: Project Finance – Special schemes
Scheme | Scheme details | Number of Units | Sanction (Cr) | Disbursements(Cr)
Financial Assistance to Govt. Contractors | For contractors engaged in Govt., PSUs etc. Quantum: up to 60% of contract value limited to minimum Rs.50 lakhs Repayment period : up to 3 years Interest rate: mid band in the interest band | 0 | 0 | 0
KSIDC Privilege Card | KSIDC assisted units with minimum 3 years of association Quantum: Up to 50% of outstanding amount Interest rate: Lowest rate in the interest band | 0 | 0 | 0
Caravan Support Scheme | Purchase of caravans & setting up caravan parks Quantum: 70% of cost of caravan (Rs.25 lakhs to Rs.1 crore per caravan), total up to Rs.5 crores Interest rate: Lowest rate in the interest band | 1 | 0.44 | 0

## Slide 65: Project Finance – Targets & achievement (2022-23)
Particulars | Target (Rs.cr) | Achieved (Rs.cr) | %
Sanction | 400.00 | 247.10 (65 units) | 61.78%
Disbursement | 250.00 | 106.42 | 42.57%
Recovery | 170.00 | 142.84 | 84.02%

## Slide 66: 1. Project Finance - Timeline for achievement (2022-23)
No Plan Amount Timeline Result
Specification | Sanction Amount(Cr) |  |  |  |  |  |  | 
 | TVM | Result | Kochi | Result | Calicut | Result | Total | Result
Till 30.09.22 | 50 | 78.47 (as on 15.12.22) | 65 | 77.49 (as on 15.12.22) | 25 | 13.10 | 140 | 168.63 (as on 15.12.22)
Till 31.12.22 | 75 |  | 100 |  | 50 |  | 225 | 
Till 31.03.23 | 120 |  | 180 |  | 100 |  | 400 | 

## Slide 67: 2. Project Finance - Timeline for achievement (2022-23)
No Plan Amount Timeline Result
Specification | Disbursement |  |  |  |  |  |  | 
 | TVM | Result | Kochi | Result | Calicut | Result | Total | Result
Till 30.09.22 | 30 | 49.87 (15.12.22) | 20 | 40.29 (15.12.22) | 15 | 16.25 (15.12.22) | 65 | 106.42 (15.12.22)
Till 31.12.22 | 50 |  | 50 |  | 30 |  | 130 | 
Till 31.03.23 | 100 |  | 100 |  | 50 |  | 250 | 

## Slide 68: 3. Project Finance – Action Plan for disbursement
Sl No. | Top 10 cases | Amount pending disbursement (Rs.cr) | Remarks
1 | SP Hitech Ventures | 60.00 | SBI sanctioned Rs.100 cr @6.85% interest rate against 8.35%
2 | Yans Healthcare Pvt Ltd | 45.00 | Revised project cost approved by the 329th BM. Company is yet to execute the documentation.
3 | Al-Fas Wood Products Pvt Ltd | 35.00 | Disbursement has not commenced. The Promoter is yet to submit the clarification regarding the Corporate Guarantee offered to SBI, without the consent of KSIDC & without complying with the Companies Act.
4 | Seraphine Dev Impex Pvt Ltd | 33.00 | Disbursement of Rs. 600 Lakhs started
5 | Woodon MDF Panels Pvt Ltd | 27.40 | Sanctioned during June 2022. Disbursement of Rs.15 Cr expected current year

## Slide 69: Project Finance – Action Plan for disbursement
Sl No. | Top 10 cases | Amount pending disbursement (Rs.cr) | Remarks
6 | Life Infusion Pharmacerticals Pvt Ltd | 26.00 | Disbursement start from January 2023
7 | Joy's The Beach Resorts Pvt Ltd | 25.00 | Sanction from Indian Bank is linked to collateral security issue and hence they are approaching other banks. Further disbursement is based on obtaining sanction from banks. HDFC Bank has agreed to fund.
8 | Nailah Chip Boards Pvt Ltd | 25.00 | It is learnt that Federal Bank sanctioned and disbursed loan at lower interest rate against 8.35%
9 | Silverstorm Amusement Parks Pvt Ltd | 12.78 | Disbursement of Rs.5 crores expected this year
10 | Green Vein Health Care Private Ltd | 11.50 | First disbursement of Rs. 475 Lakhs started

## Slide 70: 4. Project Finance - Timeline for achievement (2022-23)
Specification | Recovery |  |  |  |  |  |  |  | 
 | TVM |  | Kochi |  | Calicut |  | Total |  | 
 | P | I | P | I | P | I | P | I | T
Till 15.12.2022 | 17.78 | 16.73 | 63.22 | 20.04 | 4.72 | 3.81 | 85.71 | 40.56 | 126.28
Stressed Assets till 15.12.2022 | - | - | 14.37 | 2.20 | - | - | 14.37 | 2.20 | 16.56
Till 31.03.23 | 28.00 | 22.00 | 55.00 | 28.00 | 9.00 | 8.00 | 92.00 | 58.00 | 150.00
Stressed Assets till 31.03.2023 | - | - | 18.00 | 2.00 | - | - | 18.00 | 2.00 | 20.00

## Slide 71: 5. Project Finance – Outreach Programme
Sl No. | Action Plan | Time line | Result
1 | Awareness about KSIDC loan schemes among DIC interns in Panchayath/ Taluks -Trivandrum &Alappuzha : Week beginning 17.10.22 | October 30 | Awareness class conducted for all five southern district interns viz., Thiruvananthapuram, Kollam, Alappuzha, Kottayam & Pathanamthitta on 21.10.2022
2 | Facebook promotion videos of successful entrepreneurs | December 31 | List given to IP Division
3 | Presentation of KSIDC schemes in 10 seminars and setting up of 20 kiosks in industrial events | March 31 | 

## Slide 72: 6. Project Finance – New Policies/Action Plan for improving disbursements
Sl. No | Action to be taken | Timeline | Remarks
1 | Requirement of initial promoters contribution (loan could be reduced to 25% from the present 50% | Oct 22 | Matter approved in the 329th Board Meeting
2 | Steps to simplify procedure of Project Financing(Kochi Office) | Oct 22 | Matter to be placed on 330th Board Meeting for approval
3 | 2% Interest subvention scheme | Nov 22 | Taken up with Gov for 2023-24 Plan fund approval-note given to planning division

## Slide 73: 6. Project Finance – New Policies/Action Plan for improving disbursements
Sl. No | Action to be taken | Timeline | Remarks
4 | Modifications to CM Special Assistance Scheme Promoters of all age group may be considered for loan under CM special assistance Interest rate to be changed to base lending rate (Effective 4.85% floating including rebate) CM assistance scheme loan limit to be revised from Rs. 1 cr to Rs.5 cr | Nov 22 | Matter(hike in age to 70 years) approved by the 329th Board and sent for Govt approval
 |  |  | Matter approved by the 329th Board & sent for Government approval
 |  |  | Matter approved by the 329th Board and sent for Govt approval

## Slide 74: Project Finance – Additional target upon revision of CM Special Assistance Scheme
No Plan Amount Timeline Result
Specification | Sanction (Rs. Cr) |  |  | 
 | TVM | Kochi | Calicut | Total
Till 31.03.23 | 30 | 50 | 20 | 100

## Slide 75: Share Investment
Particulars | No of Company | Cost | Value as on 31.03.22
Equity -Listed Shares |  | (Rs Lakhs) | (Rs Lakhs)
Listed Shares -Joint Venture | 1 | 1364.07 | 8097.22
Listed Shares -Others | 17 | 2606.74 | 43601.73
Equity -Unlisted Shares |  |  | 
Unlisted shares Associate/JV/subsidiary | 5 | 525.56 | 525.56
Unlisted Shares-Others | 49 | 5161.95 | 1686.14
Preference Share Investments | 4 | 175.70 | 66.70
TOTAL | 76 | 10515.85 | 53977.35

## Slide 76: Share Investment : Details of Dividend
Particulars | 01.04.2010 to 31.03.2020 | 2020-2021 | 2021-22
Equity -Listed Shares | (Rs Lakhs) | (Rs Lakhs) | (Rs Lakhs)
Listed Shares -Joint Venture | 801.43 | 71.55 | 85.87
Listed Shares -Others | 7066.52 | 907.42 | 2090.88
Equity -Unlisted Shares |  |  | 
Unlisted shares Associate/JV/subsidiary | 202.66 | 0.00 | 19.12
Unlisted Shares-Others | 1157.40 | 142.48 | 2.48
Companies under liquidation | 0.00 | 0.00 | 0.00
Preference Share Investments | 0.00 | 0.00 | 0.00
Settled/Closed Companies | 503.57 | 0.00 | 0.00
TOTAL | 9731.58 | 1121.45 | 2198.35

## Slide 77: 7. Share investment- Target 2022-23: Rs.15 crores
Sl. No | Action to be taken | Timeline
1 | Develop strategies for achieving the share investment target | 30th October 2022
2 | Sanction of share capital investment of Rs.15 crores | 31st January 2023
3 | Disbursement of share capital investment of Rs.15 crores | 31st March 2023

## Slide 78: Project Finance- NPA Analysis
Particulars | 30/06/2021 | 31/03/2022 | 30/06/2022
Loan outstanding | 67323 | 81510 | 82708
Loan classified as NPA | 24372 | 15542 | 14170
Total NPA Provision | 16468 | 13938 | 13353
Gross NPA % | 36.20% | 19.07% | 17.13%
Rs. lakhs

## Slide 79: 8. Project Finance- Action Plan to reduce NPA
Sl. No | Action to be taken | Timeline
1 | Strict monitoring of loan cases to avoid further slippage | Continuing
2 | Case specific action plan to settle the existing NPAs by 31/03/2024 | 30th October 2022
3 | Develop new schemes/ OTS policy for settlement of NPAs | 31st December 2022

## Slide 80: 9. Project Finance : Sanction and Disbursement
Particulars | Target (Rs.cr) | Achieved (Rs.cr) | %
Sanction | 500.00 (400.00) | 225.38 | 45%
Disbursement | 415.00 (250.00) | 122.85 | 29.6%

## Slide 81: 2 . Action Plan-Sanction
Specification | Sanction Amount (Rs Cr) |  |  |  |  |  |  | 
 | TVM | Result | Kochi | Result | Calicut | Result | Total | Result
Till 30.09.22 | 50 | 96.97 (as on 31.12.22) | 65 | 110 (as on 31.12.22) | 25 | 17.92 (as on 31.12.22) | 140 | 225.38
Till 31.12.22 | 75 |  | 100 |  | 50 |  | 225 | 
Till 31.03.23 | 160 |  | 230 |  | 70 |  | 460 | 

## Slide 82: 3 . Action Plan Disbursement
Specification | Disbursement (Rs Cr) |  |  |  |  |  |  | 
 | TVM | Result | Kochi | Result | Calicut | Result | Total | Result
Till 30.09.22 | 30 | 62.33 (30.12.22) | 20 | 44.27 | 15 | 16.25 (15.12.22) | 65 | 122.85
Till 31.12.22 | 50 |  | 50 |  | 30 |  | 130 | 
Till 31.03.23 | 100 |  | 130 |  | 40 |  | 270 | 

## Slide 83: 4 . Comparison With Respect To Previous Years Till Dec 31st
Specifications | Sanctions (Rs Cr) |  |  | Disbursement (Rs Cr) |  | 
 | Target for the Year | Achieved Till 31st Dec | % | Target for the Year | Achieved Till 31st Dec | %
2020-2021 | 100 | 134 |  |  | 117.16 | 
2021-2022 | 100 | 95 |  |  | 68.5 | 
2022-2023 | 225 | 225.38 |  | 130 | 122.85 | 

## Slide 84: 5 . Action Plan For January 2023 to March 2023: Summary
Specifications | Sanctions |  | Disbursement | 
 | Number of Cases | Amount(Cr) | Number of Cases | Amount(Cr)
Head Office-Ravichandran, GM | RTL – 4 CM Scheme - 6 | 70 10 | 9 | 40
Ernakulam-Prashanth R, GM | 16 | 120 | 20 | 87.50
Kozhikode-Binil Kumar ,DGM | 12 | 50 | 10 | 25
Total | 38 | 258 | 35 | 176

## Slide 85: 6 . Action Plan for Sanction-Head Office-Shri Ravichandran R ,GM
Sl No | Sanctions Case/Lead | Amount (Rs.cr) | Result
1 | Pathoos Garments, Kollam | 1.00 | 
2 | Bakers Treat, Kollam | 1.00 | 
3 | Sherwin Food World, Tvpm | 0.25 | 
4 | Teleska, Kottayam | 0.90 | 
5 | Lac & Décor, Kollam | 1.00 | 
6 | Green Vein, Palakkad | 5.00 | 
7 | Days Hotel, Tvpm | 30.00 | 
8 | Stork Foods. Muvattupuzha | 35.00 | 
9 | Keltron WCTL 1 | 1.76 | 
10 | Keltron WCTL 2 | 4.00 | 
Total |  | 80.00 | 

## Slide 86: 6 . Action Plan for Sanction-Ernakulam Office-Shri Prasanth R ,GM
Sl No | Sanctions Case/Lead | Amount (Rs.cr) | Result
1 | Caspien Techparks India Pvt. Ltd. | 20.00 | 
2 | Amcon Paver tiles | 13.00 | 
3 | NEST Infra | 25.00 | 
4 | Goodbuy Soaps & Cosmetics Pvt. Ltd. | 5.00 | 
5 | Cazle Footcare | 1.00 | 
6 | Cochin Bakery | 2.00 | 
7 | Kollengode Heritage Hotels & Tourism Private Limited | 5.00 | 
8 | Biotane | 2.00 | 
9 | Fourmens Hotel | 3.40 | 
10 | Jollyflex | 5.00 | 
11 | Carnet Books | 2.40 | 
12 | Cisco Footcare | 4.50 | 
13 | Yentrans Maritime Logistics | 5.00 | 
14 | Ozean Seafood | 5.00 | 
15 | Tharu & Sons | 4.20 | 
16 | Kalloor Electronics & Lighting | 5.00 | 
17 | Others | 12.50 | 
Total |  | 120.00 | 

## Slide 87: 6. Action Plan for Sanction-Calicut Office-Shri Binil Kumar,DGM
Sl No | Sanctions Case/Lead | Amount (Rs.cr) | Result
1 | Crystal Aluminium-Takeover | 10.00 | 
2 | VM Polytechs-Takeover | 10.00 | 
3 | Yizle Furniture-Takeover | 10.00 | 
4 | Poovar Ayurveda Centre & Hospital | 15.00 | 
5 | Karimb Resort | 2.00 | 
6 | Osian Hotels | 5.00 | 
7 | Diary project, Kasargod | 2.00 | 
8 | Plywood unit, Kasargod | 4.00 | 
9 | PVR Healthcare | 5.00 | 
Total |  | 63.00 | 

## Slide 88: 7 . Action Plan for Disbursement-Head Office-Shri Ravichandran R ,GM
Sl No | Disbursement Case | Amount (Rs.cr) | Result
1 | Kairali Steels & Alloys | 7.00 | 
2 | Al Fas Wood Products Private Limited | 14.00 | 
3 | Razas Food Products | 4.00 | 
4 | Green Vein Healthcare | 4.00 | 
5 | Flavorasia Food Products | 1.40 | 
6 | Quality Metal Industries | 0.50 | 
7 | Jithar Enterprises | 0.65 | 
8 | Keltron | 8.76 | 
Total |  | 40.31 | 

## Slide 89: 7. Action Plan for Disbursement-Ernakulam Office-Shri Prasanth R ,GM
Sl No | Disbursement Case | Amount (Rs.cr) | Result
1 | Sun Aquatic | 4.01 | 
2 | Silver Storm | 3.00 | 
3 | Caspien Technology-PL + Takeover | 15.00 | 
4 | Amcon Paver tiles-Takeover | 13.00 | 
5 | NEST Infra-Project Loan | 15.00 | 
6 | Goodbuy Soaps-WCTL | 5.00 | 
7 | Cazle Footcare | 0.50 | 
8 | Cochin Bakery | 2.00 | 
9 | Biotane | 1.00 | 
10 | Fourmens Hotel | 2.00 | 
11 | Jollyflex | 1.00 | 
12 | Carnet Books | 2.40 | 
13 | Sisco Footcare | 4.20 | 
14 | Yentrans Maritime Logistics | 5.00 | 
15 | Ocean Seafood | 2.00 | 
16 | Taru & Sons | 5.00 | 
17 | Other | 10.00 | 
18 | Sun Aquatic | 4.01 | 
Total |  | 90.00 | 

## Slide 90: 7 . Action Plan for Disbursement-Calicut Office-Shri Binil Kumar,DGM
Sl No | Disbursement Case | Amount (Rs.cr) | Result
1 | Crystal Aluminium-Takeover | 10.00 | 
2 | VM Polytechs-Takeover | 10.00 | 
3 | Yizle Furniture-Takeover | 10.00 | 
4 | Life Infusion | 3.00 | 
5 | Southern Veneres | 2.00 | 
6 | Other | 1.00 | 
Total |  | 36.00 | 

## Slide 91: Team 4 - Start Up and We Mission
Prasanth R ,GM I/c
Nithesh B, Manager
Vinu K R, Project Officer

## Slide 92: We Mission
Started in 2017-18
Rs.25 Lakhs Loan to scale up to women entrepreneurs
Total 27 enterprises supported till 2022-2023(total loan Rs 500 Lakhs)
Budget for 2022-23 is Rs.250 Lakhs. Re-Appropriation of Rs. 150 lakhs requested from Start-Up Schemes.
Disbursed Rs.217.25 lakhs to 12 units
Pending disbursements (active)Rs. 138.60 Lakhs(extra 2-3 cases under active consideration).
Expected fund requirement for FY 2022-23 - Rs. 400 lakhs

## Slide 93: Start Up Scheme
Seed funded started in 2015 and Scale up fund started on 2021.
Seed Fund started in 2015 -Rs.25 Lakhs- Sanctions till now:130 Start-Ups
Scaleup started on 2021-Rs. 50 lakhs -Supported 9 start-ups
To be repaid in 3 years(current RBI bank rate for seed fund 6.50% and 7% for scale-ups)
Budget for 2022-23 is Rs. 700 Lakhs
Disbursed Rs. 201.64 Lakhs. Pending disbursements/applications (Active cases) - Rs. 552 lakhs
9. Total expected disbursement during the FY 2022-23 Rs. 550 lakhs. (Rs.150 Lakhs proposed to be re-appropriated to We Mission Scheme)

## Slide 94: Start Up Future Plans
Scale-Up Support Scheme of Rs.1 crore (currently Rs. 50 Lakhs) in 2023-24 Financial Year.
Publicizing KSIDC Start-Up Schemes through various means.

## Slide 95: Team 5 - Infrastructure Development
Shri. Unnikrishnan G, GM
Shri. Jose Kurian M, DGM (Kuttiyadi & KIS)
Shri. Binil Kumar MT, DGM (MFP)
Shri. Biju BG, DGM (LSP)
Smt. Suni PS, AGM (All parks, IGCs and LSP)
Smt. Sini Azeez, Manager (IGC Cherthala, MFP & KCCL)
Shri. Anush Joseph, Manager (KIZ, Angamaly, WE space)
Shri. Bivin Babu P, Deputy Manager (Kuttiyadi & KIS, IGCs-Kannur, Kozhikode)
Project Engineers
Mr. Shehas A Shukkur - LSP
Mr. Afsal KP – MFP & IGC Cherthala
Mr. Suraj J J – LEIP Palakkad
Ms. Revathy Haridas - IGC Kozhikode & Kuttiyadi Park
Ms. Anjaly C R, KIS Kasargod & IGC Kannur
Ms. Athira – Kakkanad & Angamaly

## Slide 96: Infrastructure Common Policy
Sl. No | Action to be taken | Timeline | Remarks
1 | Reducing number of LAR case |  | 
a | IGCs - 49 cases | 05 - Dec 22 19 - March 23 34 - Sept 23 49 - March 24 | Two LAR cases at IGC were disposed. Hearing of 1 case at Cherthala held on 14.12.22. Reposted Hearing conducted on 24.01.23. 14 LAR cases at Kannur were disposed off. Action being initiated for filing IA. DC Kannur issued letters to Sp. Tahsildar (LA) on 27/01/2023.
b | LSP (Phase 1) -18 cases | 9 - Sept 23 18 - March 24 | 
 | LSP (Phase 2) -13 cases | 6 - Sept 23 13 - March 24 | 
2 | GO for Covid Samashwasa extension | Sep 2022 | File is currently with Min (Fin). A G.O expected to be issued by end of February 2023.

## Slide 97: Infrastructure Common Policy
Sl. No | Action to be taken | Timeline | Remarks
3 | Auditing of Park accounts | July / Aug 2023 | IGCs accounts are regularly audited every year. Completed audit on IGC for FY 2021-22
4 | Monthly monitoring of fund status | Monthly | Monthly Funds status of IGCs and parks are readily available.
5 | Identification of 100 acres of land in 14 districts. A total of 1000 acres to be identified. | Land identification in 3 districts by Dec 2022 Land identification in 2 more districts by Mar 2023 | Land identified at Ernakulam, Alapuzha and Kasargode Districts. Land details of Palakkad district are ready at LA-Dy.Collector office and will be sent directly to KSIDC Tvm office before 10th Feb 23.

## Slide 98: Infrastructure Common Policy
Sl. No | Action to be taken | Timeline | Remarks
6 | Identification of Good units with relevant details in Industrial parks for creation of social media stories | Identification of 20 units along with all details by December 2022 | List of 40 units prepared. Details in a uniform format being prepared
7 | Survey of Industrial units | Survey to commence by Mid December 2022 To be completed by January 31st | Mr. Manuel Joe Nixon of Rajagiri School of Management was given the assignment. Data collection over. Compiling of data in progress.

## Slide 99: Revenue Details of Parks/ IGCs
Sl. No | Name of the Park | Monthly revenue from each park |  | Cumulative Internal Accruals as on 31.01.23 | Amount envisaged for any work, if any |  | Remarks
 |  | Lease Premium | Rent |  |  |  | 
 | Rs. In Lakhs |  |  |  |  |  | 
1 | IGC Cherthala | 32.52 | - | 10,383.19 |  |  | 
2 | IGC Calicut | 18.08 | 4.56 |  |  |  | 
3 | IGC Kannur | 24.76 | 11.45 |  |  |  | 
4 | Mega Food Park | - | 2.96 | 853.33 |  |  | 
5 | LEIP Palakkad | 24.52 | 3.19 | 1,071.17 | 65 | Rs.65 lakhs for drawing dedicated feeder line from Walayar substation to KIZ Palakkad(deposit work -KSEB) | 
6 | Business Park, Angamaly (Telk land) | 27.63 | - | 275.94 |  |  | 
 | Total | 127.51 | 22.17 | 12583.64 |  |  | 
 | Average of Total receipts from Apr 2022 to Jan 2023 Cash Balance as on 31.01.2023 includes Fixed deposits and Current A/c Balance. |  |  |  |  |  | 

## Slide 100: 1. IGC Cherthala (Year: 2000; Total Land area: 194.75 acres)
176.01 acres developed. Balance 18.74 to be developed
Allottable developed land is 151.26. Of this,149.36 acres allotted to 31 units (23 projects started with 1128 employment; 8 projects under implementation).
Balance 1.90 acres of developed area to be allotted. Out of this, 96.75 cents of land can be allotted by January 2023. The remaining 93.25 cents of land is now in the puramboke category and needs to be transferred from the revenue department.

## Slide 101: IGC Cherthala - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Allotting 1.53 acres (60 cents + 93 cents Purambokku) of already developed, but not allotted area. This is now 1.90 acres since after re-alignment of the new road the plot size has increased by 36.75 cents (96.75 cents + 93.25 cents Purambokku) | Oct 2022 | Proposal for 96.75 cents of land was placed in DILAC. Allotment letter will be issued after receiving the minutes of DILAC meeting. Discussed with revenue department to get 93.25 cents under purambokke assigned in our name. It is informed that our request has been forwarded to District Collector and through a G.O land will be transferred. Follow up letter sent in this regard to Thahsildar and District Collector Alappuzha
2 | Developing 18.74 acres of undeveloped land with internal roads, compound wall, open drain, storm water drain, utility duct (Rs. 10.85 Crores - M/s. Chandy’s Homes) | July 2023 | Work commenced at site. Work is temporarily suspended due to trade union issue (settled), KSEB clarification on shifting tower and importantly material shortage.

## Slide 102: IGC Cherthala - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
3 | Allottable area out of 18.74 acres (approximate 16 acres) to be leased out. | Dec 2024 | Land allotment can be started by July 2023. 5 acres by Dec 2023, another 5 acres will be allotted by March 2024 and 6 acres by September 2024

## Slide 103: IGC Cherthala - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
4 | Acquisition of KSITIL land | July 2023 | An extent of 27.95 acres (out of 33.44 acres) to be obtained back at a reasonable rate. A meeting was conducted b/w officials of KSIDC and KSITIL on 23rd December 2022 at KSITIL office, Cherthala. KSIDC had requested them to give back the land at the same / lesser price at which it was sold to KSITIL.
5 | Status of earth/ soil heap/ pile |  | Discussed with Mining & Geology Dept for advice on mining.
6 | Creche Unit | Feb 2023 | Work completed. Nirmithi Kendra yet to submit the utilisation certificate and hand over of facility. Building ready for inauguration. In discussions with Panchayat and Kudumbasree regarding running of the facility

## Slide 104: 2. Mega Food Park Cherthala (Year: 2015; Total Land area: 84.03 acres)
68.03 acres developed. Balance 16 acres to be developed
Allottable developed land is 55.27 acres. Entire area allotted to 31 units (3000 employment potential-employment generated 800).
SDF (Two buildings - Single storied -20,012 sq. ft and 9000 sq. ft)
15,617 sq. ft. allotted to 2 units (140 employment)
Balance 13,395 sqft to be allotted by Feb 2023

## Slide 105: Mega Food Park - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Developing 16 acres of undeveloped land with road, compound wall, utility duct in 16 acres (Rs. 7.46 crores & Roopam Engineers) | May 23 | Original schedule March 23. Work delayed by 2 months due to Monsoon.Now work is temporarily suspended due to material shortage. Work progress 20 - 30%
2 | Allotting allottable area out of 16 acres | Dec 23 | Land allotment is expected to be started by June 23 and allottable area (approx. 12 acres) is expected to be fully allotted by Dec 23. Applications received for more than 10 acres.
3 | SDF allotment of balance 13,395 sq. ft built-up space | Feb 23 | Allotment at SDF building can be fully completed by Feb’ 23. Proposal for 7207 Sq.ft was placed in DILAC and allotment letter will be issued after receiving the minutes of meeting. Proposal received for additional 4517 Sq.ft which will be placed in next LAC. Balance 1670 sq. ft will be allotted by Feb’23.

## Slide 106: Mega Food Park - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
4 | Commencement of O & M of : |  | 
a | Deboning Unit | 2nd week of Feb 2023 | O & M RFP released and received 2 bids. On approval, work order will be issued by the end of February 2023.
b | Deep freezer Unit | 2nd week of Feb 2023 | O & M RFP released and received 2 bids. On approval work order will be issued by the end of February 2023.

## Slide 107: Mega Food Park - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
5 | PPC Vypin | Feb 23 | Cancellation/Termination letter issued. Existing Contractor submitted the final bill on last week of January 2023. With recommendation of KITCO the final bill will be forwarded for settlement. Subsequently the work will be retendered after finalising the balance work. The retendering can be done by end of February 2023.
6 | PPC Munabam | Jan 23 | Yet to receive approval from Harbour Engineering Department. We are exploring to exclude the PPC at Munambam from Mega Food Park.
7 | PPC Thoppumpady | Feb 23 | Kerala State Nirmithi Kendra, PMC for the project, has submitted revised proposal for rate escalation from DSR 2016 to 2018. Further action to be decided on the matter, as it is similar case to PPC Vypin and the file submitted for the same.

## Slide 108: 3. IGC Kannur (Year: 2001; Total Land area: 250.00 acres)
177.5 acres developed. Balance 72.50 to be developed
Allottable developed land is 136.54 acres. Of this,118.13 acres allotted to 77 units (1848 employment).
Balance 18.41 acres to be allotted.
SDF (One four storied building and one two storied with total area of 1,28,073 sq.ft)
75,182 sq. ft. allotted to 6 units (967employment)
Balance 52,891 sq. Ft. to be allotted

## Slide 109: IGC Kannur - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Allotting 18.41 acres of already developed, but not allotted area | 4 acres - Sep 22 6 acres - Dec 22 8.17 acres- Mar 23 | 4.5 acre allotted in Sep 22. 15 applications totaling 25.30 acres received.
2 | Developing 72.50 acres of undeveloped areas (Rs.1400 lakhs – part 1) | Dec 22 - Dec 23 | M/s Credible Management appointed as PMC. Detailed estimate received. TS is expected to be obtained by mid March 23.
3 | Allotting allotable area out of 72.50 acres | 15 acres -Mar 24 30 acres-Mar 25 27.5 acres-Mar 26 | 

## Slide 110: IGC Kannur - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
4 | Allotting 52,891Sq. ft. built up space | 20,000 sq ft- Sep 23 20,000 sq ft- Mar 24 12,891 sq ft- Jun 24 | Separate entrance to SDF building to be constructed. PMC (Structures India @ 6 %) already appointed and design finalized. Estimates being prepared. Meeting in the presence of PS (Industries) conducted with M/s Maryan apparels on 20th of December 2022
5 | Dedicated Water Supply line (2KM) by KWA worth 1.34 crore | Oct 22-Sep 23 | Fund transfer submitted to treasury account of KWA. KWA is also revising the estimate to combine the work of water supply line to hostel facility. Revised estimate expected by end of Feb 23.

## Slide 111: IGC Kannur - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
6 | Reconstruction of Internal Roads (Rs.370 lakhs & Mr. Ahammed Haris B -Contractor) | June 22- Mar 23 | Work started but delayed due to incessant rain, 4 months delay and completion expected in March 2023. Rectification works w.r.t variations in GSB thickness completed. Reworked area of initial 750m reported to CTE on 03/02/23, for laying WMM. The balance area being completed in half portions.

## Slide 112: 4. IGC Kozhikode (Year: 2010; Total Land area: 310.71 acres)
159.25 acres developed.
Allottable developed land is 121.70. Of this,117.19 acres allotted to 82 units (2889 employment).
Balance 4.51 acres to be allotted
SDF (One four & two three storied building with total area of 99,927 Sq ft)
84,612 sq. ft. allotted to 10 units (210 employment)
Balance 10,625 sq. Ft. to be allotted

## Slide 113: IGC Kozhikode - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Allotting 4.51 acres of already developed, but not allotted area | 2.14 acres - Nov 22 2.37 acres - March 23 | 0.59 acres allotted in Oct. 1.55 acres can be allotted by Feb 23. (1 application for 0.85 acres being placed in next LAC and other 2 applications by the month end) 2.37 acres comes under low-lying /dispute land
2 | Allotting 10,625 Sq. Ft. Built up space, | 10,625 sq ft- Oct to Dec 22 | 10,625 Sq. Ft. has been allotted
3 | Allotting 29,383 sq. ft to CFTI |  | Government has directed that the loss in revenue may be made up from plan funds for the year 2023-2024.

## Slide 114: IGC Kozhikode - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
3 | Dedicated Water Supply line (2KM) by KWA worth 10 crores expected | Estimate by KWA – Dec 22 Amount to be paid – June 23 Completion date – June 24 | KWA submitted an estimate of Rs.16.50 Crores for the work. Estimate is being checked and for further discussion with KWA.
4 | Internal Road, Drainages, Rainwater harvesting ponds and water supply lines in 160 acres worth 13.53 cr (Contractor – Mr. Ahammed Haris B) | April 22- April 23 | Work progressing at site, but road work is delayed due to incessant rain. Hence delay of 2 months expected (June 23)
5 | DPR of remaining 5.5 acres of land | Jan 2023 | Decided to allot the land to takers.

## Slide 115: 5. Investment Zone, Palakkad (Year 2013; Total Land area: 34.05 acres)
34.05 acres developed.
Allottable developed land is 25.39 acres . Allotted entire allottable land to 29 units on Dec 22.
SDF (Two three storied building with total area of 1,17,000 sqft )
Allottable area is 80,828 sq. ft
58550 sq. ft. Allotted to 16 units.(Allotted 6953 sq.ft in Jan 23)
Balance 22278 sq. Ft. to be allotted

## Slide 116: Investment Zone, Palakkad - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remark
1 | Allotting 3.78 acres of already developed, but not allotted area | 1.78 acre - Oct 22 2 acre - March 23 | Balance 3.78 acres allotted in Dec 22. 37 Cents now available –will be allotted by March 23
2 | Allotting 34,184 Sq. Ft. Buildup space | 5000 sq. ft - Oct 22 10000 sq ft - Mar 23 10000 sq ft - Sep 23 9184 sq ft - Mar 24 | 6953 Sq.ft allotted in Jan 23. Application received for 4949 sq.feet (will be allotted in Feb 23)
3 | Installation of Transformers for power distribution worth 0.25 cr | Sep 22 | Work Completed
4 | Drawing 22kv dedicated feeder line worth 0.65 cr | Mar 23 | Entrusted to KSEB and deposited Rs.67.60 lakhs with KSEB on 29.12.22. Work to be commenced.

## Slide 117: 6. Business Park, Angamaly (Year 2022; Total Land area: 11.71 acres)
11.71 acres developed.
Alottable developed land is 9.44. Of this, 4.60 acres allotted to M/s Muralya Dairies(265 employment).
Balance 4.84 acres has also been allotted to M/s Hot Pack packaging Industries Pvt Ltd (employment -100) in October 2022. (Lease premium to be paid by H-Pack.Due date was on 15.01.23)

## Slide 118: Business Park, Angamaly - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Allotting 4.60 acres to Muralya Group | March 2022 | Party remitted applicable 20% upfront Lease premium. License agreement executed –Sep 22 Initial layout plan submitted. Site clarence works and marking trees are progressing at site.
2 | Allotting balance 4.84 acres to M/s Hotpack group | Oct 2022 | Allotted. Last date for remitting upfront lease premium -15.01.23 (Lease premium to be paid by the company)

## Slide 119: 7. Women Entrepreneurs Apparel Park -Angamaly
Total Built up space: 42,228 sqft
For setting up export oriented garment/apparel units by women entrepreneurs
Allottable area is 41,359 sqft. Of this, 20,756 allotted to 2 units .
Balance 20603 sq. ft to be allotted
Total Project Cost Rs 10.62 Crs.
Grant Assistance from ASIDE Scheme GOI - Rs 10 Cr

## Slide 120: Women Entrepreneurs Apparel Park -Angamaly - Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Allotting balance 20603 sq. ft | 5000 Sq.Ft-Oct 22 15603 Sq.ft-Mar 23 | 5000 Sq.ft will be taken up by Bumberry Baby products (P) Ltd. The space can be allotted by March 2023

## Slide 121: 8. Business Incubation Cum Office Complex Building Kakkanad (Total land : 1.51 acre leased from KINFRA)
Appointed KITCO as PMC after receiving proposals from our empaneled agencies)
Estimated amount - Rs 35.49 Cr.
KMRL is proposing metro station in 33 cents in KSIDC land.(earlier -21 cents).The frontage required is 75 m( total frontage is 120.10 m).
Integrated project is being proposed for construction of office complex building and KMRL station.

## Slide 122: Business Incubation Cum Office Complex Building Kakkanad- Action Plan for 2022 - 23
Sl. No | Action to be taken | Timeline | Remarks
1 | Obtaining TS for the Project | Oct 22 | The project can be progressed only after the integrated project proposal is submitted by KMRL.
2 | Obtaining AS for the Project | Nov 22 | 
3 | Tendering and Award of Work | Feb 23 | 

## Slide 123: 9. Industrial Park Kutiyadi
Total Land-115.13 acres
KITCO submitted a Utilization report and identified requirement of multi product park with Food Processing, Coconut based value added products and value added products from local Agriculture products as core sectors
Planning to allot 5 acre Land by Dec 2024

## Slide 124: Industrial Park Kutiyadi
Sl. No | Action to be taken | Timeline | Remarks
1 | Presentation of Masterplan by KITCO (Fee is Rs.17.05 lakhs) | Nov 22 | Based on the discussion on 23/12/2022, KITCO presented revised masterplan on 10/01/2023 ( Now what is the action Plan?)
2 | Construction of compound wall, main gate and allied works –Rs. 7.51 cr | Dec 23 | Laying of foundation stone by Minister – 17th December 2022 Tender released. Work will be awarded to L1 bidder before 10/02/2023.
3 | Construction of Internal Road, Drains -Rs 20 Cr | June 24 | PMC to be appointed after approval of masterplan

## Slide 125: Industrial Park Kutiyadi
Sl. No | Action to be taken | Timeline | Remarks
7 | Auction of Rubber Trees | Feb 23 | Communicated with Rubber Board for valuation of the rubber trees. Valuation to start by this month end. Discussion with Social Forestry completed and formal letter submitted for conducting valuation. Two follow up meetings conducted in Jan 23.

## Slide 126: 10. Industrial Space Kasargod
Total Land-1.99 acres
Land was with Astral Watches subsidiary company of KSIDC and same was transferred to KSIDC before the company was wound up.
Construction of Compound wall completed. Further infrastructure development works entrusted to KITCO.
After Stakeholder meeting requirement for a Built-up space identified and PMC appointed for 1,00,000 Sq. ft. SDF

## Slide 127: Industrial Space Kasargod
Sl. No | Action to be taken | Timeline | Remarks
1 | Construction of SDF – Rs.40 Crore | Dec 22- Dec 24 | KITCO appointed as PMC. Detailed estimate submitted by KITCO. The estimates are being vetted and made ready for TS Committee
2 | Reconstruction of Compound Wall-Rs. 0.31 Crore. (Contractor Mr. Aboobacker Siddique B I) | Nov 22 | Work Completed and bill submitted to treasury for release

## Slide 128: 11. Electronics Hardware Park
In 2012 GoK accorded AS for acquiring 100 acres of land for Electronic Hardware park at Ambaloor Ernakulam.
KSIDC received Rs 54.47 cr and acquired 11.87 acres of land and given 50 % advance for another 9 acres.
Amount utilized 21.7 crores
An expert committee during 2021, concluded that land is not suitable setting up of Electronic Hardware Park
As per Gov direction to find alternate projects, approached Fisheries dept for utilization of acquired land for viable projects .
Fisheries dept informed site is prima facia suitable for Aqua Park project.
Proposal for transfer of land is being send to Govt for consideration.

## Slide 129: Electronic Hardware Park
Sl. No | Action to be taken | Timeline | Remarks
1 | Obtaining final report from Fisheries dept and approval of the same | Nov 22 | Its been delayed. MD to remind fisheries Director
2 | Transfer of land to Fisheries dept | march 23 | Letter to Govt reg: transfer proposal is ready.

## Slide 130: Team 6 - Waste to Energy
Harikesh PC, Project Director
Saleena , Project Coordinator
Sree Prathima Devi,Manager
Lakshmi B R, Manager Coordination
Sreedevi M, Research Assistant

## Slide 131: Waste to Energy Projects
KSIDC is entrusted as the nodal agency on behalf of LSGD to take steps for the development of the 9 WtE projects in the state as a PPP project on DBFOT model.
The steps involved are;
Bid documentation and tender process
Selection and approval of concessionaire
Execution of concession agreement and legacy waste removal.
DPR preparation and approval
Power Tariff Fixation and PPA execution

## Slide 132: Waste to Energy Projects
The steps involved are; cont..
6. Statutory clearance and approvals for the project
7. Detailed Engineering and selection of contractors
8. Financial Closure- Equity and Debt
9. Construction Management-2 years
10. Operation and maintenance -25 years
Concessionaire selected for 6/9 projects, 3 projects in. Stage 3- Concession Agreement and 3 projects in stage 8-Financial Closure

## Slide 133: Waste to Energy Projects
Sl. No | District | Location | Status | Commencement of construction –Stage 9 | Result
1 | Kozhikode | Njeliyanparambu-12.6 acre | Stage 8/10 : Financial closure Progressing | Feb 2023 | 
2 | Palakkad | Kanjiokode-11 acre | Stage 8/10 :Financial closure Progressing | April 2023 | 
3 | Kollam | Kureepuzha-7 acre | Stage 8/10 :Financial closure Progressing | May 2023 | 
4 | Kannur | Chelora-9 acre | Stage 3/10 :Legacy waste Removal | Dec 2023 | 

## Slide 134: Waste to Energy Projects
Sl. No | District | Location | Status | Commencement of construction –Stage 9 | Result
5 | Ernakulam | Brahmapuram 20 acre | Stage 3/10 :Concession Agreement Executed | Oct 2024 | 
6 | Munnar, Idukki | Nallathani 2 acre | Stage 3/10 :Concession Agreement Executed |  | 
7 | Malappuram |  | Land not yet handed over to KSIDC |  | 
8 | Thiruvananthapuram |  | Land not yet handed over to KSIDC |  | 
9 | Thrissur |  | Land not yet handed over to KSIDC |  | 

## Slide 135: Team 7 - Sabarimala Airport
G Unnikrishnan GM I/c
Ratheesh S, AGM

## Slide 136: Sabarimala Airport
Proposed Location-Cheruvalli estate is 153.34 acre. |  |  | 
Sl. No | Action Plan | Timeline | Result
1 | Submission of TEFR to MOCA |  | Completed
2 | Completion of Geo Technical Investigations | Dec 2022 | 
3 | Site Clearance from MOCA | Dec 2022 | 
4 | Engagement of Agency for DPR | Jan 2023 | 

## Slide 137: Sabarimala Airport
Sl. No | Action Plan | Timeline | Result
5 | Initiation of Land Acquisition | Jan 2023 | 
6 | Clearance from Ministry of Defence | Jan 2023 | 
7 | Environment Clearance | June 2023 | 
8 | DPR Completion | June 2023 | 

## Slide 138: Team 8 - HR & Admin
Suresh Kumar, CS & Head (Legal,CA & HR)
Lakshmi T Pillai, Manager (HR & Admin)
Ashik Sheik,Manager ( Ernakulam Office )

## Slide 139: KSIDC Strength of Employee
36 Officers against sanctioned strength of 45
30 Personals in staff category against the sanctioned strength of 63
85 employees on contract

## Slide 140
Sl. No | Description | Timeline | Result
1 | Conduct 4 training before March | Mar | Three completed & one proposed on 06.02.2023
2 | Conduct pending promotions before October | Oct | Completed
3 | Exposure Visit for Contract staff | Feb | In progress
4 | Fill vacancies of 5 Assistant Manager |  | In Progress
5 | Staff Promotion policy | Feb | In progress with CMD
6 | Increasing number of permanent employee |  | Pending with Govt.
Action Plan

## Slide 141
Sl. No | Training Programme | Timeline (2022-23)
1 | Field Visit and Data Analysis 1. Visit to 2 Industrial units not assisted by KSIDC 2. Study of Industrial/Investment promotion/facilitation activities of other states and analyse systems and best policies 3. Provide innovative ideas and suggestions which can be adopted by KSIDC and the State of Kerala | Aug-Sep
2 | One day Workshop on Team Building , Motivation and Staying Positive for all Employees of KSIDC (in batches) | Oct-Nov
Training

## Slide 142
Sl. No | Training Programme | Timeline (2022-23)
3 | One day Experience sharing session with Four Eminent personalities who are best in their respective Domain in Kerala ( Best Industrialist / Best Public Servant from Police Force/Best Actor/ Best Stand Up Comedian/ Best Social Worker /Best Motivation Speaker/ Best Leadership Trainer/ Best Author/ Best Poet etc) | Planning for 2023 -24
4 | Field Visit and Data Analysis for the Executives on Contract basis 1.Visit to one Panchayath Office , one Block office and Corporation Office in Trivandrum District 2.One day workshop on Personality Development 3. One day visit to 2 industrial units | Feb-March
Training

## Slide 143: THANK YOU

## Slide 144: Strength of Employees -Permanent
Sl. No | Cadre | Sanctioned Strength | Inposition | Vacancy
1 | Managing Director | 1 | 1 | 0
2 | Executive Director | 1 | 0 | 1
3 | General Manager | 3 | 0 | 3
4 | Deputy General Manager | 7 | 7 | 0
5 | Assistant General Manager | 9 | 9 | 0

## Slide 145
Sl. No | Cadre | Sanctioned Strength | Inposition | Vacancy
6 | Manager | 11 | 11 | 0
7 | Deputy Manager | 10 | 8 | 1
8 | Assistant Manager | 4 | 1 | 3
9 | Staff Category | 63 | 28 | 35
10 | Contigent | 10 | 7 | 3
Strength of Employees -Permanent

## Slide 146
Sl. No | Cadre | In Position | Additional Requirement | Remark
1 | Accountant | 7 | 0 | 
2 | Advisor /LA Admin | 5 | 1 | Notification issued for RBI Advisor
3 | Business Development Associate/Executive | 13 | 10 | Notification issued
4 | Project Engineer | 5 | 3 | Appointment order issued
5 | Project Executive | 13 | 0 | 
Strength of Employees -Non Permanent Category

## Slide 147
Sl. No | Cadre | In Position | Additional Requirement | Remark
6 | Project Officer-Seed Fund | 1 | 0 | 
7 | Project Director W2E | 1 | 0 | 
8 | Manager Technical/Cordination W2E | 1 | 0 | 
9 | Project Coordinator W2E | 1 | 0 | 
10 | Research Assistant | 1 | 0 | 
Strength of Employees -Non Permanent Category

## Slide 148
Sl. No | Cadre | In Position | Additional Requirement | Remark
11 | Secretarial Executive | 1 | 0 | 
12 | IT Consultant | 0 | 1 | Notification issued
13 | Content Creator cum writer | 0 | 1 | Notification issued
14 | Web Designer | 0 | 1 | Notification issued
15 | System Admin | 1 | 0 | 
Strength of Employees -Non Permanent Category

## Slide 149
Sl. No | Cadre | In Position | Additional Requirement | Remark
16 | Executive Assistant | 1 | 0 | 
17 | Stenographer | 5 | 0 | 
18 | Support Staff( Driver/Messenger etc ) | 13 | 0 | 0
Strength of Employees -Non Permanent Category